## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Backend,Database prarvin
| Member Name | Shraddha Panchal
| PRN No | 210543181102
Description
2 | Role | Frontend
| Member Name | Chakradhar Karhale
| PRN No | 210543181037
| Description | Managed all Frontend, jsp pages
3 | Role | Backend
| Member Name | Pravin Patange
| PRN No | 210543181061
| Description | Managed all backend functionality

## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Crop Prediction System |  | 30 Day | 2021-08-23 | 2021-09-22 | 2021-09-27
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-23 | 2021-08-23 | 1 Day
1.2 | Finish webpage | 2021-08-24 | 2021-08-26 | 2 Day
1.3 | Project Design | 2021-08-23 | 2021-08-28 | 6 Day
2 | Coding
2.1 | Phase 1 | 2021-08-29 | 2021-09-05 | 8 Day
2.2 | Phase 2 | 2021-09-06 | 2021-09-13 | 8 Day
2.3 | Additional Features | 2021-09-17 | 2021-09-17 | 2 Day
3 | Testing
3.1 | Phase 1 Testing | 2021-09-17 | 2021-09-17 | 1 Day
3.2 | Modification /Any changes | 2021-09-18 | 2021-09-18 | 1 Day
3.3 | Phase 2 Testing | 2021-09-19 | 2021-09-19 | 1 Day
3.4 | Modification /Any changes | 2021-09-20 | 2021-09-20 | 1 Day
3.5 | Final Testing | 2021-09-21 | 2021-09-21 | 1 Day
4 | Documentation
4.1 | User Guide | 2021-09-22 | 2021-09-24 | 2 Day
4.2 | Presentation | 2021-09-27 | 2021-09-27 | 1 Day